## Backlog
ID | Workstream | Task | Priority | Dependency | Acceptance Criteria | Status
B-001 | Data access | Obtain approved dataset and data dictionary | P0 | Coordinator/data owner | Authorized source and version recorded | Pending
B-002 | Identity | Confirm stable user identifiers and joins | P0 | Engineering | Join rules documented and tested | Pending
B-003 | Events | Approve event taxonomy and required properties | P0 | Product/Engineering | Tracking plan signed off | Proposed
B-004 | Quality | Implement primary key, null, enum, timestamp, FK tests | P0 | Data Engineering | Tests run in CI or scheduled job | Proposed
B-005 | Metrics | Approve KPI definitions and exclusions | P1 | Product/Finance | Metric owners approve definitions | Proposed
B-006 | Pipeline | Build raw/staging/mart pipeline | P1 | Source access | Reproducible refresh with lineage | Proposed
B-007 | Dashboard | Implement approved dashboard pages | P2 | KPI signoff | Filters, definitions and freshness visible | Proposed
B-008 | Governance | Approve retention, access and deletion controls | P0 | Legal/Privacy | Policy and access matrix approved | Pending
B-009 | Monitoring | Configure freshness/volume/schema alerts | P1 | Pipeline | Alerts tested with owner routing | Proposed
B-010 | Rollout | Pilot with product and operations users | P2 | Dashboard and QA | UAT sign-off and issue log closed | Proposed